Program

Yarra Community Centre (YYC) runs a variety of programs for the community and its youth. Our Youth Mentoring Program will support many students in year 11 and who attend our homework club, to make an efficient transition into tertiary studies by providing each of the students with a RMIT student mentor.

Youth mentoring program supports will include:

- Monthly mentoring session

- Career advising

- Campus tours

- Events

- Guest speakers

To be eligible for the Youth Mentoring Program, the student must be part of The Homework Club at Yarra Community Centre and be enrolled in Year 11 studies.

Program Objectives

- Increase stakeholder relationships by 20% by 25 November 2021

- Gain strong alliances and relationships with stakeholders

- Increase number of students in Homework Club to be eligible for the Youth mentoring program

- To develop new skills and knowledge in young people such as:

- Build confidence and self esteem

- Time management and organisation skills

- Work on communication skills with peers, adults and public speaking

Stakeholders

| Year 11 students | Attending program, co-program designers (clients) |
| --- | --- |
| RMIT students | Mentors |
| YYC members | Coordinators of the program |
| Career/Course counsellor | Counsel year 11 students |
| Teachers | Help year 11 students with better grade outcomes |
| Local and Federal government | Funding bodies |
| Philanthropist organizations | Funding bodies |
| Parents | Support for year 11 students |

Implementation schedule

| Priority | Task | Resources required | Timing | Person responsible |
| --- | --- | --- | --- | --- |
| 1 | Consult and engage | Engagement plan Rmit students Year 11 students YYC staff | 2-4 weeks | YYC |
| 2 | Implementation | Templates Program outline | 2 days | YYC |
| 3 | Policies and procedures |  | 1 day | YYC |
| 4 | Funding applications |  | 2-4 weeks | YYC |
| 5 | Hire staff and mentors |  | 1-2 weeks | YYC |
| 6 | Training of mentors and volunteers | Food and drink, projector, space to conduct training, info packs | 2 days | YYC |
| 7 | Marketing and Advertising |  | 3 days | 3rd party company |
| 8 | Match students with mentors |  | 1 day | YYC |
| 9 | Implement mentoring sessions |  | ongoing | YYC |